## Log
FORGE 16A and 16B Stimulations. April 2024
Time | All times in this log are local time
All seismic times in the Divine traces are UTC BUT displayed as local time
Reference Point | Ground level at 16A
[7 empty] | Levels | Components | Traces | To
Tools | 56 | PSS |  |  |  |  | 1 | 3 | 1 | 3
| 78B | Geochain | 8 levels at 100ft intervals |  |  | 3C | 8 | 3 | 4 | 27
| 58 | VSI | 12 levels at 50ft intervals |  |  | 3C | 12 | 3 | 28 | 63
| 16B | DAS |  |  |  | 1C | 499 | 1 | 64 | 562
| Delano | DAS | GES Neubrex interrogator |  |  | 1C | 439 | 1 | 563 | 1001
Public Trace Data
[7 empty] | Levels | Components | Traces | To |  |  |  |  | Nominal trace order
| 56 | PSS |  |  |  |  | 1 | 3 | 1 | 3 | Traces in the public Seg2 files |  |  |  | VEN
| 78B | Geochain | 8 levels at 100ft intervals |  |  | 3C | 8 | 3 | 4 | 27 |  |  |  |  | VEN
| 58 | VSI | 12 levels at 50ft intervals |  |  | 3C | 12 | 3 | 28 | 63 |  |  |  |  | No data
| 16B | DAS |  |  |  | 1C | 1496 | 1 | 1 | 1496 | Traces in the public SegY files |  |  |  | N/A
Trace amplitude is positive for energy propagating in the directions up, +x, +y
Processing Cabin | At 78B
Fibre optic network connection from 16 pad to 78B for DAS
23rd March | PSS in 78B was pulled - working
25th March | PSS deployed in 56
28th March
11:30 | Deploying Geochain
| Temperatures |  | 125°C | on first deployment
Put the Geochain on a UPS
78B, group 8, trace 3 has positive going noise offsets every few hundred milli-seconds
29th March
9:00 | On site
The noise spikes have gone
Checked and found the noise spikes were present prior to the UPS installation so were not due to over heating as speculated
All groups seem to be working correctly and responding to tap tests
Tested setting the gain as 42 vs 54dB. The background noise levels were very similar and the noise perfectly well sampled.
Concluded no need to use high gain and so obtain greater dynamic range
PJ/BK tracked down a 60Hz noise problem and fixed it
An earth strap to the wellhead is being installed to ensure this is a long term fix.
30th March - Saturday
8:45 | On site
VSI questions. SLB can only offer 2000Hz and 1.5s records
31st March - Sunday
9:30 | Clock time on the PSS made an error switching due to a summertime clock change.
Merged PSS and Geochain files from 1:00AM to 09:30 are likely to be mis-matched by an hour
this is not worth correcting as we are only testing at the moment
Power supply to the new fibre network at 56 is unstable and trips periodically.
2nd April
15:00 | SLB reveal they are unable to provide realtime SegY data. It's also not clear if they can provide any realtime data even in their own LDF format
18:00 | Checked the Geochain sync usng a hammer and the time break recorder
| delta T seems to be faster than the tube wave |  |  |  |  | 630 | ms
| delta T is Group 1 arrival - time break |  |  |  |  | 604 | ms
[6 empty] | 600 | ms
Also checked the Delano and 16B interrogators
3rd April
9:10 | Noise levels |  | Geochain | +-5 | uV
|  |  | PSS | +-0.5 | uV
|  |  | 16B | +-5-10 | Unknown units |  | Noise level is quite variable
|  |  | Delano | +-2 | Unknown units
10:15 | Stage 3R | Pumps on
| 6000 psi | 32 BPM
10:35 | 6200 psi | 50 BPM
10:32 | First event
11:43 | Cycle the Geochain to reset the clock
12:25 | 5000 psi | 50 BPM
| Neubrex summary |  | Frac hits at 9810ft and 9770ft MD rKB
Plug at 9857ft in 16A MD rKB
| Source | 1451 | 9770 | ft
|  | 1886 | 9810 | ft
Stage 4 Perf shots
16:14 | Perf shot | 10070 | 10076 | ft rKB
16:15 | [9 empty] | Starts |  |  |  | End
[9 empty] | Stage | Report |  | Divine |  | Report |  | Divine
[9 empty] | 3R | 3rd April | 10:12 | 9:44 | 3rd April | 3rd April | 13:57 | 17:57 | 3rd April
19:00 | Remi and Dimitrios on the night shift | [7 empty] | 4 | 3rd April | 17:55 | 17:57 | 3rd April | 3rd April | 21:02 | 22:35 | 3rd April
[9 empty] | 5 | 4th April | 0:46 | 22:35 | 3rd April | 4th April | 3:20 | 6:30 | 4th April
4th April | [8 empty] | 6 | 4th April | 6:30 | 6:30 | 4th April | 4th April | 16:48 | 13:38 | 4th April
[9 empty] | 7 | 5th April | 0:32 | 13:38 | 4th April | 5th April | 9:11
| Stage 4 | Sources 1-993 were overwritten in error with later events | [6 empty] | 8 | 5th April | 13:44 |  |  |  | 22:01
6:30 | Stage 5 | End
| Stage 6 | Start
7:10 | The pump rate is low and pressure high. The formation is tight and not fraccing
[9 empty] | Perf depths rKB 16A |  | One |  | Two |  | Three |  | Four |  | Five |  | Six |  | Seven |  | Eight
[9 empty] | Stage | Mid point | Top | Bottom | Top | Bottom | Top | Bottom | Top | Bottom | Top | Bottom | Top | Bottom | Top | Bottom | Top | Bottom
[9 empty] | 4 | 10073 | 10070 | 10076
13:36 | 16B re-opened | [7 empty] | 5 | 10023 | 10020 | 10026
16:48 | End of Stage 6 according to the Post Job report | [7 empty] | 6 | 9964.5 | 9970 | 9976 | 9959 | 9962 | Additional un-planned perfs due to tight formation
[9 empty] | 7 | 9848 | 9898 | 9901 | 9850 | 9853 | 9798 | 9801
13:38 | Stage 6 | End | [6 empty] | 8 | 9632.5 | 9720 | 9723 | 9695 | 9698 | 9670 | 9673 | 9645 | 9648 | 9620 | 9623 | 9595 | 9598 | 9570 | 9573 | 9545 | 9548
| Stage 7 | Start | [6 empty] | 9 | 9406.5 | 9490 | 9493 | 9470 | 9473 | 9445 | 9448 | 9420 | 9423 | 9395 | 9398 | 9370 | 9373 | 9345 | 9348 | 9320 | 9323
[9 empty] | 10 | 9273 | 9270 | 9276
Remi and Dimitrios on the night shift
5th April
0:32 | Stage 7 Start
13:44 | Stage 8
Poor weather. Very windy
14:00 | Around this time the PSS in 56 failed.
17:00 | Changed the PSS surface panel. No changed
Tested the wireline. It seems to be Ok so maybe a tool fault
Too late and too windy to replace it
Remi and Dimitrios on the night shift
6th April - Saturday
1:00 | Stage 9. Begin pumping
6:00 | On site
A couple of Mw 1s overnight
8:00 | Two >1Mws in the last hour (06:53 onwards)
Paul and BK pulled the PSS tool from 56
20:57 | Stage 10. Begin pumping.
7th April - Sunday | Day 98
6:30 | On site
10:00 | Replaced the PSS tool
11:40 | 56 is detecting events again
8th April
04:15:00 to 05:30 | Jarring operations in 16B at |  |  | 9772-9774 ft |  | From the 16B daily report No. 26
9787-9790 ft
Eclipse day
Followed up with Neubrex and Monty Keown regarding the preparations for deploying the fibre optic wireline in well 58-32
14:30 | No flow observed at 56. PJ checking the PSS
UTC
|  | Observed | Rig | GES | Rig | Rig | Rig | GES
|  |  | Stage 4 | Stage 5 | Stage 6 | Stage 7 | Stage 8 | Stage 9
|  |  | 3rd April | 4th April | 4th April | 5th April | 5th April | 6th April
|  |  | 22:14 | 4:57 | 11:21 | No times | 17:40 | 5:45 | UTC
|  |  | 22:14 | 4:58 | 11:23 | Between | 17:42 | 5:47
|  |  | 22:15 |  |  | 02:30 and | 17:44 | 5:48
[6 empty] | 5:45 | 17:46 | 5:50
[7 empty] | 17:48 | 5:51
[7 empty] | 17:51 | 5:51
[7 empty] | 17:52 | 5:52
[7 empty] | 17:53 | 5:53
5:54
Local Times
|  |  | Stage 4 | Stage 5 | Stage 6 | Stage 7 | Stage 8 | Stage 9 | Stage 10
|  |  | 3rd April | 3rd April | 4th April | 4th April | 5th April | 5th April | 6th April
|  |  | 16:14 | 22:57 | 5:21 | No times | 11:40 | 23:45 | 9:21
|  |  | 16:14 | 22:58 | 5:23 | Between | 11:42 | 23:47
|  |  | 16:15 |  |  | 20:30 and | 11:44 | 23:48
[5 empty] | 11:40 | 23:45 | 11:46 | 23:50
[5 empty] | Re-shoot |  | 11:48 | 23:51
[7 empty] | 11:51 | 23:51
[7 empty] | 11:52 | 23:52
[7 empty] | 11:53 | 23:53
23:54
9th April
9:00 | Checked the PSS was clamped. The waveforms generally look more seismic. The vertical in particular has increased amplitude and is similar to the horizontals
10:30 | Let 10ft slack onto the PSS tool in 56
Released the crane
Wayne made up the following splices on the fibre optic wireline
SM 1 spliced to the broken length SM 2
SM 3 and SM 4 spliced to coreless fibre
MM 1 spliced to MM 2
PJ/BK attempted to make up the tool but were unable to apply sufficient torque with the available tools
Seek new spanners tomorrow to continue
10th April
9:00 | Geochain has failed overnight. Restart around 09:30
Data merging and auto-processing also stopped. One laptop was a windows restart.
Geochain temperatures were normal. This has no particular meaning with regard to the power failures
|  |  |  | 2024-04-03 | 2024-04-10
| Noise levels |  | Local Times Stage 4: Geochain; Local Times Stage 5: +-5; Local Times Stage 6: +-3; Local Times Stage 7: uV
|  |  | PSS | +-0.5 | +-1 | uV
|  |  | 16B | +-5-10 | +-15 | Unknown units |  | Noise level is quite variable
|  |  | Delano | +-2 |  | Unknown units
16:03 | Perfs fired
17:10 | Geochain off to investigate the clock problem
17:35 | Geochain on
18:02 | Geochain off. It failed for an unknown reason but manually re-started OK
18:18 | Geochain On.
22:00 | Return
| 16B Perfs |  | Local Times Stage 8: Measured Depth (Referenced to KB = 32 ft)
|  |  | Local Times Stage 4: Gun 1; Local Times Stage 6: Gun 2; Local Times Stage 8: Gun 3; Local Times Stage 10: Gun 4 |  | Gun 5 |  | Frac Plug Top
| Frac Plug #1 | [11 empty] | 9777 | Mid point
| Stage 1 (16B) |  | Local Times Stage 4: 9769-9773; Local Times Stage 6: 9756-9760; Local Times Stage 8: 9745-9749; Local Times Stage 10: 9690-9694 |  |  |  |  | 9731.5
Frac Plug #2
| Stage 2 (16B) |  | Local Times Stage 4: 9,508 - 9,512; Local Times Stage 6: 9,475 - 9,479; Local Times Stage 8: 9,459 - 9,463; Local Times Stage 10: 9,447 - 9,451 |  | 9,429 - 9,433 |  |  | 9470.5
Frac Plug #3
| Stage 3 (16B) |  | Local Times Stage 4: 9,389 - 9,393; Local Times Stage 6: 9,343 - 9,347; Local Times Stage 8: 9,265 - 9,269 |  |  |  |  | 9327
Frac Plug #4
| Stage 4 (16B) |  | Local Times Stage 4: 9,054 - 9,058; Local Times Stage 6: 9,026 - 9,030; Local Times Stage 8: 8,995 - 8,999; Local Times Stage 10: 8,958 - 8,962 |  |  |  |  | 9006
Frac Plug #5
| Stage 5 (16B) |  | Local Times Stage 4: 8,879 - 8,883; Local Times Stage 6: 8,870 - 8,874; Local Times Stage 8: 8,834 - 8,838; Local Times Stage 10: 8,774 - 8,778 |  |  |  |  | 8826.5
11th April
4:00 | Fraccing Stage 16B Stage 1 | bar: Local Times Stage 4
5:30 | End
16:14 | Re-clamped groups 1, 5 and 8 of 78B
12th April
16:45 | Geochain ping test. All channels are normal
13th April - Saturday
6:00 | On site
Stage 2 16B
14th April - Sunday
8:27 | Geochain tool 7 failed. Re-started but is noisy
Various fails and re-starts
Discovered that the tool 8 data is written to traces 19, 20 and 21 when tool 7 fails (this is referred to as "bypass" in Avalon software)
11:39 | Tool 7 is back on.
15th April
6:00 | Perfs |  | Local Times Stage 4: (9389-9393'), gun 2 (9343-9347'),; Local Times Stage 7: gun 3 (9265-9269').
| Perfs mid depth |  | Local Times Stage 4: 9329
14:25 | Start 16B Stage 3 (approximate time) | bar: Local Times Stage 4 to Local Times Stage 5
Water dripping slightly from 78B
16th April
23:08 | Perfs | 8958'-8962', 8995'-8999', 9026'-9030' and 9054'-9058'
| Perf mid depth |  | Local Times Stage 4: 9008
17th April
6:03 | 16B Stage 4
7:30 | Extreme Wireline Inc. are at 58 ready to prepare thefibre optic wireline deployment
The pressure on 58 is rising
11:00 | 58 pressure at 180psi
Delay on BOSS deployment due to lugs on the dummy exceeding the ID of one of the wellhed components
Rollins will machine the hole to allow the dummy to pass
13:00 | Running downhole in 100ft lifts
This operation took fully
| 2 | Experienced Extreme staff | Local Times Stage 6: Clay and Ben
| 2 | Extreme site hands | Local Times Stage 6: Harry and Kasin
| 1 | Paul Jaques
| 1 | Jim Rutledge
| 1 | Crane driver
| 1 | Ben Dyer
| 1 | Avalon engineer | Local Times Stage 6: Heng
Equipment was a simple spooler, measuring head, packoff pipe over the packoff to provide a landing for the wireline clamp
18:30 | At approximately 7300ft meassured depth
19:30 | All tidied at the wellhead and left site
18th April
Geochain failed overnight. Reported by Ben K. from the UK
2:40 | Merger stopped due to missing Geochain files
Re-triggered the data with only one group and two traces required ie the PSS
9:30 | Attempting to re-start the Geochain
9:30 | Delano is turned off to move the Neubrex to 58. Wayne and Dimitrios are working on it.
11:00 | Geochain telemetry unit seems to have failed. The arms are out and cannot be retracted.
Pulling back may cause damage to the arms but there is no other option.
12:20 | Winch spooling arm problem
Sorting out the depth of the fibre optic wireline
Geochain worked briefly with a spare telemetry unit at the surface and chain downhole.
It failed during testing with the number 8 tool arm out
19:00 | Finished pulling the Geochain
19th April
8:30 | Checking the depth of the fibre optic wireline in 58
15:00 | Pulled up the 58 wireline dummy into the casing.
20th April - Saturday
21st April
9:00 | Tools are running
16B halted for a few hours overnight
| Trace levels | +-
| 58 DAS | 3 | Local Times Stage 4: units
| 16B DAS |  | Local Times Stage 4: units
78B PSS | bar: Local Times Stage 4
56 PSS | bar: Local Times Stage 4
17:00 | Severe noise on the 58 DAS. Found the wireline had been kinked.
The water truck operators had moved the wireline and pulled a kink in it where there had been a torque induced loop
17:50 | The noise problem stopped and it appears the wireline had been straightened.
Performed a wellhead hammer test to check the fibre
A strong tube wave was observed to 6000ft and a reflection as if this was the bottom of the well
Checked the fibre length on the Neubrex and it was 3812m? As on deployment
The fibre seems to be intact
19:30 | Departed
22:54 | Small event
22nd April
8:30 | Checked the triggers overnight and found an event at 22:54:02
This was detected over the whole 58 DAS wireline length confirming the fibre is intact
Heng has dis-assembled one of the Geochain tools. There is significant pitting of the O ring seats on the arm shaft bushes
It was also found that there is something rattling in the electronics section. (Later identified as desicant)
12:51 | Testing SM 1 of the 58 fibre with hammer strikes
13:15 | Testing SM 2 of the 58 fibre with hammer strikes
The S/N seems to be similar on both fibres so leave SM 2 connected to compare them in overnight, quiet periods
23rd April
21:49 | 16B was off
24th April
1:40 | 16B is back
25th April
9:00 | Guiding the digger to trench in the wireline at 58
9:00 | Pulling 78B. Turned it off the trigger
12:00 | Trench prepared at 78B for fibre network line
26th April
9:30 | Buried the 58 wireline and tidied the land link fibre to the inl cabin
2nd May | Terminated the strain monitoring at midnight local time

## Well 56 PSS
Borehole | 56-32
56-32 | Single PSS tool
| Serial Number | 005
Corrected depths remove an error in the Avalon winch depth measurement
The correction is only applicable to the depth to the Top tool. The ITC lengths are not affected
| Correction factor | 1.005
|  | MD ft bGL | Corrected ft bGL
| Depth | 5052 | 5077.3869
| Gain downhole | 500 | 54dB
| Gain in DCP | 2
| Minimus data acquisition | 12s records
Continuous, gapless sequence
| Channel | Nominal Geophone Sensitivity = 1 x 52 | Combined Coil Resistance 25degC | Coil Resistance 150degC | Attenuation due to 3k48 damping resistor | Sensitivity V/m/s | Amplifier Gain (54dB) | DCP Gain | Combined Gain | scale to uV | Factor to remove gain | Overall factor to uV | PSS Sensitivity V/m/s | Divine factor to um/s
| Z | 52 | 2458 | 4092.867 | 0.45954 | 23.8958 | 491 | 2 | 982 | 1000 | 0.0010183 | 1.0183 | 23465.7125 | 0.042615
| X | 52 | 2465 | 4104.5229 | 0.45883 | 23.8591 | 492 | 2 | 984 | 1000 | 0.0010163 | 1.0163 | 23477.3688 | 0.042594
| Y | 52 | 2447.9 | 4076.0493 | 0.46056 | 23.949 | 491 | 2 | 982 | 1000 | 0.0010183 | 1.0183 | 23517.9408 | 0.042521
| Polarity | Energy propagating Up, East and North produces a positive response
Factor
| To scale to uV | mV to uV | 1000
|  | remove gain | 0.0010183
25th March | Tool deployed
5th April | Tool failed
7th April | PSS replaced with SN 001 | Same spec as SN 005 as above
| 11:40 | Detecting events after this time

## Well 58 DAS
Borehole | Activity
58-32 | SLB VSI 12 level 3C string
| Top tool | 4585 | ft bGL
| Bottom tool | 5135 | ft bGL
| Intervals | 50 | ft
Tool failed. Some data may be available.
58 DAS in wireline
| Excess fibre length | .38 to .42% | see Massimo 31/10/2023
| Scaling factor | 1.0291 | trace spacing at nominal 1m
2024-04-17 | Deployed using a crane to approximately 7300ft bGL
Optical measurements
| OTDR wireline length measured at surface with the dummy tool attached prior to deployment | [5 empty] | 3704.844 | m | 12155 | feet | From Wayne Fishback, NBX
2024-04-18 | In hole measurements | Total length from INL cabin to dummy |  |  |  |  | 3812.7 | m | 12508.8583 |  | Measured from NBX interrogator
This value includes the scaling factor
|  | Approximate length to the wireline clamp |  |  | Trace | 1506 | 1549.8384 | m
|  | Wireline clamp |  |  |  |  | 2 | m | aGL
|  | Downhole |  |  |  |  | 2260.8616 | m | 7417.525 | ft | bGL
Acquisition setting
| Top acquisition depth | 2311.75 | m |  |  | length on fibre
|  | 3812.75 | m
|  | ft bGL | m | Trace from TD at 1m spacing
| Perf | 6550 | 1996.44 | 293.8272
| Perf | 6962 | 2122.0176 | 168.2496
| Casing shoe | 7342.5 | 2237.994 | 52.2732
| Dummy | 7417.5 | 2260.854 | 29.4132
| TD | 7514 | 2290.2672 | 0
2024-04-19 | Pulled the wireline up ~100ft
| Detected the tension rise on entering the casing |  |  | bGL | rKB
| Set the dummy 20ft above the casing shoe at |  |  | 7322.5 | 7344 | ft
| Number traces |  |  | 491 |  |  | MD bGL
| Length |  |  | 1512.7905 | m | 4963.2233 | ft
| Top trace |  | Trace 1 |  |  | 2359.2767 | ft
| second trace |  | Trace 2 |  |  | 2369.4058 | ft
| Bottom trace |  | Trace 491 |  |  | 7322.5 | ft

## Well 78B Geochain and PSS
Borehole | Activity
78B-32 | Deployment of 8 level 3C Geophone string. Geochain
Operation of the Geochain data acquisition
Winch - Avalon skid mount
Crane for upper sheave wheel during deployment/movements only
Engineer ASL, BK and Joe Rawlings
Geochain output is sequential, 12 second SegY files with GPS time stamps in real time
| KB is | 30.4 | ft aGL
2024-03-27 | Deployed with top tool ~300ft below surface to monitor overnight
2024-03-28 | Deployed to depth. Measured depths are relative to GL. NB trajectory reference in Divine is rKB ie add 30.4ft to the MD bGL for tool depths in Divine
Corrected depths remove an error in the Avalon winch depth measurement
The correction is only applicable to the depth to the Top tool. The ITC lengths are not affected
| Correction factor | 1.005
|  | MD ft bGL | Corrected bGL | MD ft rKB | Corrected rKB
11:30 | Top tool | 4866 | 4890.4523 | 4896.4 | 4921.005 | 135 | °C | 275 | F
| Bottom Tool | 5566 | 5590.4523 | 5596.4 | 5621.005 | 150 | °C | 302 | F
6ft of slack run in
Avalon Geochain X
8 levels
100ft intervals
3C per level.
4 sensors per component
Geospace Omni 2400, 198V/m/s overall, 47kohm damping
| Divine scale factor to um/s |  |  | 5050.5051 | 4807.6923
|  |  | HIS |  |  | Temperature record
| String MD rKB ft |  | Inclination | Roll |  | 29th March | 30th March | 31st March | 1st April
14:00
| TAS |  |  |  |  | 115 |  | 115 | 115
| CFU | [6 empty] | 114 | 114
| 1 | 4866 | 2.6 | 70.9 |  | 124 |  | 123 | 123
| 2 | 4966 | 2.7 | 232.7 |  | 119 |  | 118 | 118
| 3 | 5066 | 1 | 96.9 |  | 122 |  | 121 | 121
| 4 | 5166 | 1.2 | 217.3 |  | 126 |  | 125 | 126
| 5 | 5266 | 1.6 | 173.6 |  | 127 |  | 126 | 126
| 6 | 5366 | 0.5 | 274.2 |  | 128 |  | 127 | 127
| 7 | 5466 | 1 | 35.5 |  | 130 |  | 129 | 129
| 8 | 5566 | 4.1 | 114.2 |  | 135 |  | 135 | 135
| Sensitivity | 208 | 4 x 52 V/m/s
File units are volts
| Divine factor | 4807.6923
Toolstring 78B-32
| Surface System |  |  | Install date | 2024-03-27
| GSP | 144 |  | Well | 78B
| GMP | 35 |  | Depth (Top Tool) | 4866ft
| PC | Field7
| Head: |  | W.P | 4xW
| TAS XT | 304
| DFU | 51
| Tool | ASR | Digitiser AS272-XTB | Sensor ASR-227XT |  | ITC | Length ft/m | W.P.
[6 empty] | 1839 | 100ft | 4xW
| 1 | 955 | 1599 | 297
[6 empty] | 1843 | 100ft | 4xW
| 2 | 957 | 1604 | 309
[6 empty] | 1837 | 100ft | 4xW
| 3 | 568 | 1607 | 303
[6 empty] | 1842 | 100ft | 4xW
| 4 | 894 | 1601 | 302
[6 empty] | 1841 | 100ft | 4xW
| 5 | 963 | 1621 | 298
[6 empty] | 1835 | 100ft | 4xW
| 6 | 994 | 1612 | 296
[6 empty] | 1834 | 100ft | 4xW
| 7 | 956 | 1618 | 172
[6 empty] | 1838 | 100ft | 4xW
| 8 | 1005 | 1616 | 300
[6 empty] | 183? | 100ft | 4xW
| VRS | 232
| ASR-89 | 5
2004-04-18
2:40 | Tool failed
Tool removed from the borehole
2004-04-19 | Preparing PSS tool SN002 for deployment | ft bGL | ft bKB | ft bGL | ft rKB
| Deployed to | 5566 | 5596.4 | 5593.9698 | 5624.3698 | Corrected depth
Channel | Nominal Geophone Sensitivity = 4 x 52V/m/s | Combined Coil Resistance 25degC | Coil Resistance 140degC | Attenuation due to 11.8k damping resistor | Amplifier Gain at 140degC | DCP Gain | Combined Gain | PSS Sensitivity V/m/s
Z | 208 | 9565.6643 | 15313.0343 | 0.43522 | 489 | 2 | 978 | 88533.2
X | 208 | 9592.6218 | 15356.1888 | 0.43452 | 489 | 2 | 978 | 88392.5
Y | 208 | 9627.1154 | 15411.4072 | 0.43364 | 489 | 2 | 978 | 88213.1
| Sensitivity | Damping | Overall | Amplifier | DCP | Gain | Divine factor to uV |  | Divine to um/s
Z | 208 | 0.43522 | 90.5247 | 489 | 2 | 978 | 1.0225 |  | 0.011295
X | 208 | 0.43452 | 90.3809 | 489 | 2 | 978 | 1.0225 |  | 0.011313
Y | 208 | 0.43364 | 90.1975 | 489 | 2 | 978 | 1.0225 |  | 0.011336
2024-04-25
9:00 | Pulling the PSS tool